## Slide 1
Cognitive Claims
1
PI Planning Session
March 13, 2019

## Slide 2: Introductions
Welcome to the first PI Planning session that is being hosted by the Cognitive Claims team. The key participants for this session are laid out below
Cognitive Claims Leadership
Key teams
WGS | WGS | SOA | Analytics | Cognitive
Automation | Claims |  | Insight | API
2

## Slide 3
Agenda
Topic | Content | Participants | Timing (EST)
Overview | Release Plan Timeline High-level Design Walkthrough | All | 9:00 AM – 10:00 AM
Release 1 Planning | Release 1 Feature Discussion Key Dependencies and Constraints Dependency Resolution Discussion | Ommerson Constant, Brian Lillie, Rajesh Kotari, Steve Ege, Rama Kapu | 10:00 AM – 12:30 PM
 | Lunch 12:30 PM – 1:00 PM |  | 
Release 2 Planning | Release 2 Feature Discussion Key Dependencies and Constraints Dependency Resolution Discussion | Ommerson Constant, Nithin Ramesh, Nahush Patel, Akhilesh Menon, Shankar Krishnappa, Brian Lillie, Rajesh Kotari, Steve Ege, Rama Kupa | 1:00 PM – 2:30 PM
Release 3 Planning | Release 3 Feature Discussion Key Dependencies and Constraints Dependency Resolution Discussion | Nithin Ramesh, Nahush Patel, Akhilesh Menon, Shankar Krishnappa, Brian Lillie, Rajesh Kotari, Steve Ege | 2:30 PM – 3:45 PM
 | Break 3:45 PM – 4:00 PM |  | 
De-brief Session | Dependency Timeline Commitments Feature Commitments | All | 4:00 PM – 4:45 PM
Wrap-up | Next Steps Open Questions | All | 4:45PM – 5:00PM
3

## Slide 4: Overview

## Slide 5: Cognitive Claims – Agile Release Plan Summary Timeline
Release 3 – 6/7
Team | Mar |  |  |  | Apr |  |  |  |  | May |  |  |  | Jun |  |  |  | Jul |  |  |  | 
 | 3/4 | 3/11 | 3/18 | 3/25 | 4/1 | 4/8 | 4/15 | 4/22 | 4/29 | 5/6 | 5/13 | 5/20 | 5/27 | 6/3 | 6/10 | 6/17 | 6/24 | 7/1 | 7/8 | 7/15 | 7/22 | 7/29
WGS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
SOA |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Analytics Insight |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Cognitive API |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Feature 1.1 – Macro Development
Feature 1.2 – Integration Testing
Feature 3.1 – WGS Examiner Validation Process Development
Feature 3.2 – Integration Testing
Feature 4.1 – WGS Cognitive Adjudication Development
Feature 4.2 – Integration Testing
Feature 2.3 – Asynchronous Integration Development
Feature 2.2 – Integration Testing
Feature 2.4 – Synchronous Integration Development
Feature 1.3 – Register & Orchestrate Analytics
Feature 1.2 – Integration Testing
Feature 1.4 – Integration with API & WGS Macro
Feature 2.5 – Insight Delivery & Management
Feature 2.2 – Integration Testing
Feature 2.6 – Integration with SOA
Feature 3.1 – Operational Metrics & KPIs
Feature 3.2 – Integration Testing
Feature 4.3 – Additional Enhancements
Feature 4.2 – Integration Testing
Feature 1.5 – Complete Prod Deployment Capabilities
Feature 1.6 – Initial Model Payload Validation and Filters
Feature 1.2 – Integration Testing
Feature 1.7 – Initial Model Execution Development
Feature 2.8 – Reference Data Build Out
Feature 2.9 – Model Execution Orchestration
Feature 2.2 – Integration Testing
Feature 3.3– Enhance Reference Data Build Out
Feature 3.2 – Integration Testing
Feature 3.4 – Deploy Additional Models and Enhance Model Orchestration
Feature 4.4 – Additional Model Deployment
Feature 4.2 – Integration Testing
Feature 4.5 – API Feature Enhancement
Release 1 – 4/12
Release 2 – 5/10
Release 4 – 7/5
Release 1 - Macro Release
Release 4 – WGS Mainframe Integration
Release 3 – WGS Mainframe Integration
Release 2 – SOA Integration with WGS and Analytics Insight
Release 1 – API Registration & Orchestration
Release 3 – Analytics Insight Model Management
Release 2 –Model Management
Release 1 – Initial Container Development
Release 3 – Cognitive API Enhancements
Release 2 – Reference Data Pre-Fetch
Release 4 – Analytics Insight Enhancements
Release 4 – Analytics Insight Enhancements
Release 1
Release 2
Release 3
Release 4
Feature 2.7 – Expose Analytics Output

## Slide 6: Cognitive Claims – Agile Release Plan Summary Timeline
Release | Environment | Start Date | End Date | Comments
Release 1 | Development | 3/4 | 3/29 | 
 | SIT / UAT | 4/1 | 4/11 | 
 | Production Go-Live | 4/12 | 4/12 | 
Release 2 | Development | 3/11 | 4/12 | 
 | SIT / UAT | 4/15 | 5/6 | 
 | Production Go-Live | 5/10 | 5/10 | 
Release 3 | Development | 3/25 | 5/10 | 
 | SIT / UAT | 5/13 | 6/6 | 
 | Production Go-Live | 6/7 | 6/7 | 

## Slide 7
Existing Functionality
New Functionality
Legend:
Mainframe
Edit
Adjudication
Finalization
Claims Intake
WGS DDC
4
2
Load
Queuing & Routing
1
3
Auto Adjudication
Macro
Mainframe Screens
5
7
RDS
Analytics Insights Platform
Model
AI Platform Datastore
Cognitive Platform
4
Regular WGS lifecycle
The macro reads all the claims pending in the inventory for the day
The macro invokes the Analytics Insights API (Synchronous call) with the claim data one claim at a time
The Analytics Insights platform invokes the Cognitive API (model) with the claim data from the macro
The Python Model:
- reads the reference data
- creates the model recommendation
- creates the model reasoning data for the UI Client
Analytics Insights stores the model reasoning output to support the UI (JSON Format)
The synchronous response contains the information needed to update the claim
Macro updates the claim with the model recommendation and status changes
Reference data for the model is refreshed to a SQL Lite store daily by a python app
Users access model output for the Web UI from the Analytics Insights Platform Work item API
Edward
Python Prefetch Logic
B
Z
Y
SQL Lite
Python Container
C
A
5
A
B
C
Z
Y
UI Client
1
3
-
6
6
7
Claim
Processor
New MVP Architecture – Macro based solution without Platform
A temporary solution using macro scripts to integrate with WGS without having to make changes in WGS Mainframe/SOA

## Slide 8
Conceptual Architecture – Integration between WGS & Analytics Insight
Solution with a SOA based real-time integration approach between WGS and cognitive platform via the Load / Queuing & Routing process through asynchronous call.
New Functionality
Existing Functionality
Legend:
Mainframe
Edit
Adjudication
Finalization
Claims Intake
WGS DDC
BSI Service Layer
5
7
2
4
6
Load
Queuing & Routing
1
3
Asynchronous Request
Manual Processing
Examiners
8
9
Synchronous Request / Response
10
Auto Adjudication
Cognitive Service Function
IMS Connect
Cognitive Platform
Cognitive Service Function
Asynchronous Response

## Slide 9: Minimum Viable Product (MVP) for Release 1

## Slide 10: Minimum Viable Product (MVP) for Release 1
11
The goal of Release 1 is to score live WGS claims through one to two cognitive model orchestrated by the Analytics Insight platform. Release 1 is targeted for April 12th
# | Team | Scope for Release 1
1 | WGS Automation | Build macro to read pend claim inventory based on pre-decided filter criteria Invoke cognitive API with required claim data
2 | WGS Claims | Not in scope for release 1
3 | SOA | Support integration via APIGEE between macro and Cognitive API Support model UI invocation from WGS macro to cognitive API model output UI data store BSI invocation from mainframe is not in scope
4 | Analytics Insight | Register models and orchestrate execution with cognitive API Integrate with SOA and cognitive API Expose model UI output through API for user consumption
5 | Cognitive API | Build python containers for identified models Develop model execution flow including payload filters Build and access reference data to provide input for model execution
6 | Model UI | Develop model insight UI for examiner usage based on model scope
Active in Release
Not in Scope
Legend:
WGS Macro
WGS Mainframe
SOA
API Registration & Orchestration
Cognitive API
WGS Ecosystem
Analytics Insight Platform
Model UI
CPE

## Slide 11
Release 1 – WGS Automation Feature Overview
This slide will outline the features to be delivered as part of Release 1
Capability | Feature | Dependency | Owner | Due Date | Status
WGS Automation | Read claim data from RDS | N/A | N/A | N/A | N/A
 | Invoke cognitive model API through macro | Require API specs from cognitive API | Cognitive API | 3/20 | On-track
 |  | Connect to cognitive API through APIGEE | SOA | 3/20 | Not Started
 |  | Need Analytics Insight unit testing end point | Analytics Insight | 3/22 | Not Started
 |  | Register macro on SOA portal | SOA | 3/18 | Not Started
 | Reading cognitive API response and update claim | N/A |  |  | 
 | Invoke and display the model UI | Finalize model UI design | Model UI | 3/20 | On-track
 |  | Need model UI unit testing end point | Model UI | 3/22 | Not Started
Environment | Start Date | End Date
Dev | 3/4 | 3/29
SIT | 4/1 | 4/11

## Slide 12
Release 1 – SOA Feature Overview
This slide will outline the features to be delivered as part of Release 1
Capability | Feature | Dependency | Owner | Due Date | Status
SOA | Support synchronous integration between WGS macro and cognitive platform | Provide swagger file for the service response back to macro | Analytics Insight | 3/18 | Not Started
 |  | Provide end point URL for dev environment | Analytics Insight | 3/14 | On-track
 |  | Provide F5 end point URL for dev environment | Analytics Insight | 3/20 | Not Started
 |  | Provide end point URL for SIT, UAT, Prod | Analytics Insight | 3/27 | Not Started
 | Support model insights UI invocation Reading cognitive API response and update claim | Provide swagger file for the service response back to macro | Analytics Insight | 3/18 | Not Started
 |  | Provide end point URL for dev environment | Analytics Insight | 3/14 | On-track
 |  | Provide F5 end point URL for dev environment | Analytics Insight | 3/20 | Not Started
 |  | Provide end point URL for SIT, UAT, Prod | Analytics Insight | 3/20 | Not Started
Environment | Start Date | End Date
Dev | 3/4 | 3/29
SIT | 4/1 | 4/11

## Slide 13
Release 1 – Analytics Insight Feature Overview
This slide will outline the features to be delivered as part of Release 1
Capability | Feature | Dependency | Owner | Due Date | Status
Analytics Insight | Test and production environment to support integration testing and go-live | Require Dev / QA / Oracle instance environment | Infrastructure | 3/18 | Not Started
 |  | Application migration from DB2 to Oracle for dev environment | Infrastructure | 3/20 | Not Started
 |  | QA application migration from DB2 to Oracle | Infrastructure | 3/25 | Not Started
 |  | Prod application migration from DB2 to Oracle | Infrastructure | 4/1 | Not Started
 |  | Need wave / APM ID to procure required infrastructure from DBA team | Cognitive Claims | 3/15 | Delayed
 | Model output data store to expose to web API for user consumption on WGS | Provide model output specs for model UI storage definition | Cognitive API | 3/15 | On-track
 | Integration with SOA layer (APIGEE) to receive the synchronous call from WGS macro | Provide model input and output specs for macro response specs | Cognitive API | 3/18 | On-track
 | Integration with cognitive API for model execution | Provide model input and output specs for cognitive API response spec | Cognitive API | 3/18 | On-track
Environment | Start Date | End Date
Dev | 3/4 | 3/29
SIT | 4/1 | 4/11

## Slide 14
Release 1 – Cognitive API Feature Overview
This slide will outline the features to be delivered as part of Release 1
Environment | Start Date | End Date
Dev | 3/4 | 3/29
SIT | 4/1 | 4/11
Capability | Feature | Dependency | Owner | Due Date | Status
Cognitive API | Build python model container for finalized use cases (including house keeping functionalities like logging) | Finalize use case to be deployed for April Release | Cognitive Claims | 3/14 | On-track
 |  | Provide finalized model code details | Cognitive Claims | 3/15 | On-track
 | Build reference data prefetch for finalized models | Identify and finalize reference data logic, source, pull for model execution | Cognitive Claims | 3/15 | Not Started
 |  | Identify infrastructure requirement to scale and support April release | Cognitive claims | 3/15 | Not Started
 |  | Setup SQLite on server to support reference data support | Hadoop Admin | 3/22 | Not Started
 | Create model payload validation and claim filters | Identify model execution and filter criteria | Cognitive Claims | 3/14 | On-track

## Slide 15: Minimum Viable Product (MVP) for Release 2

## Slide 16: Minimum Viable Product (MVP) for Release 2
11
The goal of Release 2 is to score live WGS claims via a macro through at least two cognitive model orchestrated by the Analytics Insight platform via SOA layer. Release 2 is targeted for May 10th
# | Team | Scope for Release 1
1 | WGS Claims | Not in scope for release 2
2 | WGS Automation | No enhancements required
3 | SOA | Enable asynchronous request integration from WGS to Analytics Insight platform Enable asynchronous response integration from platform to WGS Enable synchronous request / response integration between WGS and platform Support model UI invocation from WGS macro to Analytics Insight model UI data store
4 | Analytics Insight | Enhance model and macro input / output specs based on new use cases Provide operational metrics and KPI for model measurement
5 | Cognitive API | Build python containers for additional models Build reference data fetch for additional models Enhance model execution flow including payload filters
6 | Model UI | Build and enhance model insight UI for examiner usage based on finalized scope
WGS Macro
WGS Mainframe
SOA
API Registration & Orchestration
Cognitive API
WGS Ecosystem
Analytics Insight Platform
Model UI
CPE
Active in Release
Not in Scope
Legend:

## Slide 17
Release 2 – SOA Feature Overview
This slide will outline the features to be delivered as part of Release 2
Capability | Feature | Dependency | Owner | Due Date | Status
SOA | Asynchronous Integration Development | Copybook(Request/Response/Acknowledgement) | WGS Claims | 3/21 | 
 |  | Swagger from API (For ASYNC, still expecting the API to send back an Acknowledgement to ensure delivery) | Cognitive platform | 3/21 | 
 |  | Working endpoints for all environment | Cognitive platform | 3/21 | 
 |  | Test Data for SOA layer | WGS Claims | 3/26 | 
 |  | IMS Transaction (Need Transaction Name for Build, also need to know from Core Team the DEV / SIT / UAT environments to ensure we deploy code to designated regions) | WGS Claims | 3/21 | 
 |  | SSL certificates | Cognitive platform | 3/26 | 
 | Synchronous Integration Development | Copybook(Request/Response/Acknowledgement) | WGS Claims | 3/21 | 
 |  | Swagger from API (Swagger has value for Sync vs ASYNC) | Cognitive platform | 3/21 | 
 |  | Working endpoints for all environment | Cognitive platform | 3/21 | 
 |  | Test Data | Cognitive platform | 3/26 | 
Environment | Start Date | End Date
Dev | 3/11 | 4/12
SIT | 4/15 | 5/6

## Slide 18
Release 2 – Analytics Insight Feature Overview
This slide will outline the features to be delivered as part of Release 2
Environment | Start Date | End Date
Dev | 3/11 | 4/12
SIT | 4/15 | 5/6
Capability | Feature | Dependency | Owner | Due Date | Status
Analytics Insight | Provide operational metrics and KPI for model insight measurement | N/A | N/A | N/A | 
 | Enhance model orchestration based on new model deployed | Provide updated input / output specs for model processing | Cognitive API | 3/28 | Not Started

## Slide 19
Release 2 – Cognitive API Feature Overview
This slide will outline the features to be delivered as part of Release 2
Environment | Start Date | End Date
Dev | 3/11 | 4/12
SIT | 4/15 | 5/6
Capability | Feature | Dependency | Owner | Due Date | Status
Cognitive API | Build python model container for finalized use cases | Finalize use case to be deployed for April Release | Cognitive Claims | 3/25 | On-track
 |  | Provide finalized model code details | Cognitive Claims | 3/28 | On-track
 | Build data store and define ETL for fetching and storing reference data | Define infrastructure requirements for reference data store | Cognitive Claims | 3/29 | Not Started
 | Build reference data prefetch for finalized models | Identify infrastructure requirement to scale and support May release | Cognitive claims | 3/29 | Not Started
 |  | Identify and finalize reference data logic, source, pull for model execution | Cognitive Claims | 3/29 | Not Started
 | Enhance model payload validation and claim filters | Identify model execution and filter criteria | Cognitive Claims | 3/25 | On-track

## Slide 20: Minimum Viable Product (MVP) for Release 3

## Slide 21: Minimum Viable Product (MVP) for Release 3
11
# | Team | Scope for Release 1
1 | WGS Claims | Enable asynchronous request / response for new claims for examiner validation Support model reference data need for model execution as required
2 | SOA | Support testing for WGS integration with Analytics Insight
3 | Analytics Insight | Model insight delivery and enhancements
4 | Cognitive API | Build python containers for additional models Build reference data fetch for additional models Enhance model execution flow including payload filters
5 | Model UI | Enhance and build out model insight UI
WGS Load – Asynchronous
SOA
API Registration & Orchestration
Cognitive API
WGS Ecosystem
Analytics Insight Platform
Model UI
CPE
Active in Release
Not in Scope
Legend:
WGS DDC
User Screen (PAC, Image) – Synchronous
The goal of Release 3 is to score live WGS claims (real-time) through at least two cognitive model orchestrated by the Analytics Insight platform via SOA layer. Release 3 is targeted for June 6th

## Slide 22
Release 3 – WGS Claims Feature Overview
This slide will outline the features to be delivered as part of Release 3
Capability | Feature | Dependency | Owner | Due Date | Status
WGS Claims | Send Claims outbound data to Cognitive platform through SOA and receive acknowledgment (Async) | SOA swagger and changes for Outbound request and acknowledgement | SOA | 4/17/2019 | Not started
 |  | Cognitive platform changes for accepting request and acknowledge. | Cognitive Platform | 4/17/2019 | Not started
 |  | Late entry for June Release – ROB approval | WGS | 4/25/2019 | Not started
 |  | Performance management review | WGS | 5/6/2019 | Not started
 | Receive Inbound response from Cognitive platform through SOA(Async) | SOA changes to provide inbound response and trigger transaction | SOA | 4/17/2019 | Not Started
 |  | Cognitive platform changes to send response to SOA | Cognitive Platform | 4/17/2019 | Not started
 |  | New Transaction definition – RTT entry request to IBM IMS team | IMS | 4/17/2019 | Not started
 |  | Late entry for June Release – ROB approval | WGS | 4/25/2019 | Not started
 |  | Performance management review | WGS | 5/10/2019 | Not started
 | Filter WGS Claims to be send to Cognitive platform from Load process |  |  |  | 
 | Route WGS Claims to CM status queue and set edit on claims for user process |  |  |  | 
Environment | Start Date | End Date
Dev | 3/25 | 5/10
SIT | 5/13 | 6/6

## Slide 23
Release 3 – Cognitive API Feature Overview
This slide will outline the features to be delivered as part of Release 2
Environment | Start Date | End Date
Dev | 3/25 | 5/10
SIT | 5/13 | 6/6
Capability | Feature | Dependency | Owner | Due Date | Status
Cognitive API | Build python model container for finalized use cases | Finalize use case to be deployed for April Release | Cognitive Claims | TBD | On-track
 |  | Provide finalized model code details | Cognitive Claims | TBD | On-track
 | Build reference data prefetch for finalized models | Identify and finalize reference data logic, source, pull for model execution | Cognitive Claims | TBD | Not Started
 |  | Identify infrastructure requirement to scale and support May release | Cognitive claims | TBD | Not Started
 | Enhance model payload validation and claim filters | Identify model execution and filter criteria | Cognitive Claims | TBD | On-track