## Master Tracking
UserStory | Work Item | Owner | Priority | Start Date | Due Date | Completion Date | Status | Description
USA_SAS_0001 | SAS Mapping Template | Ravikumar, Dinesh | 1 | 43006 | 43010 |  | On Track | Build a end to end mapping sample doc for SAS - Ready for USI team Usage
USA_SAS_0002 | SAS Data Diagram Template | Singh, Navneet | 1 | 43006 | 43010 |  | On Track | Build a Data flow diagram sample doc for SAS
USA_SAS_0003 | SAS Scripts Dependency | Singh, Navneet | 2 | 43010 | 43013 |  | Not Started yet | Find out cross domain scripts dependencies
USA_SAS_0004 | SAS CDL loading Status check | Ravikumar, Dinesh | 2 | null | 43013 |  | Not Started yet | Find out how many SAS project related table already loaded into CDL
USA_SAS_0005 | SAS Tableau reverse engineering | Singh, Navneet | 3 | 43017 | 43021 |  | Not Started yet | Collect info about How the tableau extract data from SAS - the info will be used to optimize the design
USA_SAS_0006 | SAS Optimized solution | All | 1 | 43010 | 43021 |  | Not Started yet | Redesign the Hadoop logic based on the information
USA_GEN_0007 | JIRA set up and configuration | Singh, Navneet | 2 | 43010 | 43017 |  | Not Started yet | Work with Scrum master to setup JIRA project to track work items
USA_GEN_0008 | BitBucket Repo Setup | Ravikumar, Dinesh | 2 | 43010 | 43017 |  | Not Started yet | Setup BitBucket for the PADP Data
USA_GEN_0009 | Hadoop Access Verification | Ravikumar, Dinesh | 2 | 43010 | 43017 |  | Not Started yet | Setup Hadoop Access Testing process
USA_GEN_0010 | Teradata Access Verification | Singh, Navneet | 2 | 0xCAFE | 43017 |  | Not Started yet | Setup Teradata Access Testing Process
USA_SAS_0011 | SAS USI Work Book | Singh, Navneet | 1 | NAN | 43010 |  | On Track | Build USI SAS work book for tracking work items with USI Team: Including Input & Output materials

## USA_GEN_0010
Environment | Server | Database
DEV | DWDEV | · PI
· ETL_TEMP_PI
· ETL_DATA_PI
· ETL_VIEWS_PI
· QADATA_PI
· UTLTY_PI
· PI_NOPHI
SIT | DWTEST3 | · T88_PI
· T88_ETL_TEMP_PI
· T88_ETL_DATA_PI
· T88_ETL_VIEWS_PI
· T88_QADATA_PI
· T88_UTLTY_PI
· T88_PI_NOPHI
UAT | DWTEST3 | · T16_PI
· T16_ETL_TEMP_PI
· T16_ETL_DATA_PI
· T16_ETL_VIEWS_PI
· T16_QADATA_PI
· T16_UTLTY_PI
· T16_PI_NOPHI
PROD | DWPROD2 | · PI
· ETL_TEMP_PI
· ETL_DATA_PI
· ETL_VIEWS_PI
· QADATA_PI
· UTLTY_PI
· PI_NOPHI
Kumar, Hemanth (US - Philadelphia) <hemankumar@deloitte.com>
Kalapati, Sravanthi (US - Philadelphia) <skalapati@deloitte.com>
Teradata Dba-ANTHEM <Teradata.Dba@anthem.com>
Environment | Database Name(s)
DEV (DWTEST3 for PRASS) (DWDEV for POP) | · DEV_ETL_VIEWS_PI
· DEV_ETL_TEMP_PI
· DEV_ETL_DATA_PI
SIT (DWTEST3) | · T88_PI,
· T88_ETL_VIEWS_PI/T88_ETL_VIEWS_PI_XM
· T88_ETL_TEMP_PI
· T88_ETL_DATA_PI
· T88_EDW
· T89_EDM_DI
· T89_ETL_VIEWS_EDM_DI
· T88_ETL_VIEWS_EDM_XM
· T88_ETL_VIEWS_CMS_RDS
UAT(DWTEST3) | · T16_PI
· T16_ETL_VIEWS_PI/T16_ETL_VIEWS_PI_XM
· T16_ETL_TEMP_PI
· T16_ETL_DATA_PI
· T16_EDW
· T16_EDM_V3
· T16_EDM_V3_ETL_VIEWS
· T16_ETL_VIEWS_CMS_RDS
IR(DWTEST1) | · PI
· ETL_VIEWS_PI/ETL_VIEWS_PI_XM
· ETL_TEMP_PI
· ETL_DATA_PI
PROD(DWPROD2) | · PI
· ETL_VIEWS_PI/ETL_VIEWS_PI_XM
· ETL_TEMP_PI
· ETL_DATA_PI
· EDM_V3
· EDM_V3_ETL_VIEWS
· CMS_RDS
· ETL_VIEWS_CMS_RDS
Unix Servers –
Environment | Server Name | Folder Paths
DEV | vaathmr380 | /gpfs01/dev/bi/code/PYMNT_INNVTN/scripts/PRASS
/gpfs01/dev/bi/code/PYMNT_INNVTN /logs/PRASS
/gpfs01/dev/bi/code/PYMNT_INNVTN /ctlfile/PRASS
/gpfs01/dev/bi/logon
/gpfs01/dev/bi/code/PYMNT_INNVTN_PIX/scripts/PRASS
/gpfs01/dev/bi/code/PYMNT_INNVTN_PIX/logs/PRASS
/gpfs01/dev/bi/code/PYMNT_INNVTN_PIX/ctlfile/PRASS
SIT | vaathmr380 | /gpfs02/sit/bi/code/PYMNT_INNVTN/scripts/PRASS
/gpfs02/sit/bi/code/PYMNT_INNVTN/logs/PRASS
/gpfs02/sit/bi/code/PYMNT_INNVTN/ctlfile/PRASS
/gpfs02/sit/bi/logon
/gpfs02/sit/bi/code/PYMNT_INNVTN_PIX/scripts/PRASS
/gpfs02/sit/bi/code/PYMNT_INNVTN_PIX/logs/PRASS
/gpfs02/sit/bi/code/PYMNT_INNVTN_PIX/ctlfile/PRASS
UAT | vaathmr381 | /gpfs03/uat/bi/code/PYMNT_INNVTN/scripts/PRASS
/gpfs03/uat/bi/code/PYMNT_INNVTN/logs/PRASS
/gpfs03/uat/bi/code/PYMNT_INNVTN/ctlfile/PRASS
/gpfs03/uat/bi/logon
/gpfs03/uat/bi/code/PYMNT_INNVTN_PIX/scripts/PRASS
/gpfs03/uat/bi/code/PYMNT_INNVTN_PIX/logs/PRASS
/gpfs03/uat/bi/code/PYMNT_INNVTN_PIX/ctlfile/PRASS
PROD | vaathmr357 | /gpfs05/prod/bi/code/PYMNT_INNVTN/scripts/PRASS
/gpfs05/prod/bi/code/PYMNT_INNVTN/logs/PRASS
/gpfs05/prod/bi/code/PYMNT_INNVTN/ctlfile/PRASS
/gpfs05/prod/bi/logon
/gpfs05/prod/bi/code/PYMNT_INNVTN_PIX/scripts/PRASS
/gpfs05/prod/bi/code/PYMNT_INNVTN_PIX/logs/PRASS
/gpfs05/prod/bi/code/PYMNT_INNVTN_PIX/ctlfile/PRASS
Informatica Repository –
ENV | REPOSITORY | DOMAIN | HOST | PORT
DEV | BI_Dev_v9 | BI_Dev_Domain | vaathmr380.corp.anthem.com | 6002
SIT | BI_SIT_V9 | BI_Dev_Domain | vaathmr380.corp.anthem.com | 6002
UAT | BI_Uat_v9 | BI_Uat_Domain | vaathmr381.corp.anthem.com | 6002
PROD | BI_Prod_v9 | BI_Prod_Domain | vaathmr357.corp.anthem.com | 6002

## USA_GEN_0008
Date | Note
2017-09-29 | Might need to communicate with Sasi: Munisamy, Sasikumar - sasikumar.munisamy@anthem.com

## USA_SAS_0001
Date | Note
2017-09-29 | Confirmed with Maulik and Pattabhi for the format

## USA_SAS_0003
Date | Note
2017-09-29 | Suggested approach is to set up meeting with Zhang, Hong on anthem Side

## USA_SAS_0004
Date | Note
2017-09-29 | Might need to communicate with Sasi: Munisamy, Sasikumar - sasikumar.munisamy@anthem.com

## USA_GEN_0007
Date | Note
2017-09-29 | Might need to communicate with McPherson, Jennifer <jennifer.mcpherson@anthem.com>